## Sheet1
Task Description | Impact Risk | Expected Hours | Due Date | Champion | Actual Work Hours | Assigned | Task Completed | Link to doc | Notes
Task Description | Impact Risk | Expected Hours | Due Date | Champion | Actual Work Hours | Assigned | TRUE | https://drive.google.com/drive/folders/1qTHhwZLPdb6WxjiK1S6kBP1OM1yPP6RR?usp=drive_link
initial user interface design | 8 | 3 | 2024-10-31 | Savannah | 5 | Savannah | TRUE |  | must be able to interface with ESP32, not touch screen (button/potentiometer)
selecting screen | 8 | 1 | 2024-11-15 | Savannah | 1 | Savannah | TRUE | https://docs.google.com/document/d/1tmPK-S2oo9aXApMzLYQliIJt_JYLfn_S148TjRFearc/edit
Color Sensor Picking | 7 | 1 | 2024-11-03 | Astrid | 1 | Astrid | TRUE
Finalize UI V1 | 6 | 2 | 2024-11-08 | Savannah | 1 | Savannah | TRUE
ESP32: buttons interaction | 7 | 1+ | 2024-12-03 | Astrid | 2 | Astrid | TRUE
ESP32: color sensor interaction | 8 | 1+ | 2024-12-03 | Astrid | 2 | Astrid | TRUE
ESP32: temp sensor interaction | 8 | 1+ | 2024-12-03 | Astrid | 1 | Astrid | TRUE
ESP32: screen interaction | 8 | 1+ | 2024-12-09 |  | 2 | Savannah | TRUE | See Files/SharedKiCad
Shared Schematic Implementation | 8 | 1+ | 2024-11-06 | Astrid | 1 | Astrid | TRUE
Initial CAD work | 7 | 3 | 2024-03-14 | Astrid | 6 | Astrid | TRUE
Determine test strip method | 7 | 4 | 2024-11-24 | Kaye | 4 | Kaye | TRUE
Test UI on 3 subjects | 7 | 3 | 2024-11-20 | Savannah | 3 | Savannah | TRUE
Contact DON for MR | 9 | 0.5 | 2024-12-03 | Astrid | 0.25 | Astrid | FALSE
Market research | 6 | 3+ |  |  |  | All | TRUE
Develop early sensor pseudocode | 5 | 3+ | 2024-12-09 | Savannah | 2 | Savannah | TRUE
Alter UI for rectangle screen | 7 | 2 | 2024-12-01 | Savannah | 1 | Savannah | FALSE
Determine prelim test strip parts | 7 | 2 | 2024-12-04 | Kaye |  | Kaye | TRUE
remake the timeline | 4 | 1 | 2024-11-24 | Savannah | 1 | savannah | FALSE
test strip cylinder design | 8 | 7 | 2024-01-08 | Kaye | 8 | Kaye | FALSE
test strip activation design | 7 | 5 | 2024-01-08 | Kaye | 7 | Kaye | FALSE
color sensor design | 6 | 3 | 2024-01-08 | Kaye | 4 | Kaye | FALSE
initial order deadline | 4 | 2 | 2024-12-04 |  |  | Astrid | TRUE
Color sensor PCB support | 8 | 1 | 2024-12-09 | Astrid | 5 | Astrid | FALSE
Buttons PCB support | 8 | 3 | 2024-02-20 | Astrid | 5 | Astrid | TRUE
Temp Sensor PCB support | 8 | 1 | 2024-12-09 | Astrid | 3 | Astrid | FALSE
research Peristaltic pump |  |  | 2024-12-04 |  |  | Kaye | TRUE
Code: home screen | 9 | 3 | 2024-03-01 | Savannah | 1 | Savannah | FALSE
Code: settings screen | 7 | 3 | 2024-03-01 | Savannah | 3 | Savannah | FALSE
Code: history screen | 8 | 3 | 2024-03-01 | Savannah | 2 | Savannah | FALSE
Code: notifications screen | 8 | 3 | 2024-03-01 | Savannah | 2 | Savannah | FALSE
Code: inhabitants list screen | 6 | 3 | 2024-03-01 | Savannah | 1 | Savannah | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Winter Term
Task Description | Impact Risk | Expected Hours | Due Date | Champion | Actual Work Hours | Assigned | Task Completed | Link to doc | Notes
Make Rolo happy | 10 | ∞ | 2024-01-08 | Savannah | ∞ | ALL | TRUE
Code: home screen | 9 | 3 | 2024-03-01 |  |  | Savannah | FALSE
Code: settings screen | 7 | 3 | 2024-03-01 |  |  | Savannah | FALSE
Code: history screen | 8 | 3 | 2024-03-01 |  |  | Savannah | FALSE
Code: notifications screen | 8 | 3 | 2024-03-01 |  |  | Savannah | FALSE
Code: inhabitants list screen | 6 | 3 | 2024-03-01 |  |  | Savannah | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE